## 📋 RT App Migration Tracker
🚀 GBS AUTH — Real-Time App Migration Tracker ¦ CDP On-Prem → Databricks · Cloudera Kafka → AWS MSK Active-Active · Kerberos → SASL_SSL / SCRAM-SHA-512
📦 Total Platforms |  |  | ✅ Completed |  |  | 🔄 In Progress |  |  | 📋 Planned |  |  | 🌎 MSK East Region |  |  | 🌏 MSK West Region |  |  | 🔐 Auth Protocol |  |  | 📅 Last Updated
7 |  |  | 2 |  |  | 2 |  |  | 3 |  |  | us-east-1 |  |  | us-west-2 |  |  | SASL_SSL/SCRAM-512 |  |  | 2026-07-01
📌 IDENTIFICATION |  |  |  | 📂 AS-IS (On-Premises CDP) | [7 empty] | 🚀 TO-BE (AWS Cloud — Databricks) | [8 empty] | 📊 TRACKING & GOVERNANCE
|  |  |  | 📡 Application & Topic |  |  |  | 🔐 Auth & Infrastructure |  |  |  | ⚡ App, Topic & Table |  |  |  |  | ☁️ MSK Endpoints & Status |  |  |  | 👤 Ownership & Schedule |  |  |  | 📝 Technical Config & Notes
# | Platform Name | Environment | Migration Status | Existing App Name (CDP Spark) | Existing Kafka Topic (Cloudera) | Existing Table / Path (HDFS) | Existing Auth (Protocol) | Existing Kafka Cluster | CDP Cluster Host / URL | Existing Broker Port | Data Format (As-Is) | New App Name (Databricks) | New Kafka Topic (MSK) | New Delta Table (Unity Cat.) | New Auth Protocol | DBX Job Name (Struct Stream) | MSK East Endpoint (us-east-1) | MSK West Endpoint (us-west-2) | East Consumer Status | West Consumer Status | App Owner / DCS Lead | Sprint / Release | Migration Start Date | Go-Live Target Date | DBFS Checkpoint Path | Databricks Secret Scope | Downstream Consumers | Notes / Blockers
1 | 🔴 HDC | Production | ✅ Complete | HDCAuthStreamApp | hdc.auth_txn | hdfs:///data/hdc/auth_txn/ | Kerberos GSSAPI | ETIMS Cloudera Kafka | cdp-kafka-node01.corp.fiserv.net | 9092 | Parquet | HDCAuthStreamDBX | hdc.auth_txn | gbs_auth.hdc_auth_delta | SASL_SSL/SCRAM-SHA-512 | HDCAuth_StructStream_Job | b-xxxx.kafka.us-east-1.amazonaws.com:9096 | b-yyyy.kafka.us-west-2.amazonaws.com:9096 | ✅ Live | ✅ Live | Raneeth Kumar | Sprint 3 | 2026-01-10 | 2026-02-28 | dbfs:/checkpoints/hdc_auth_txn | dcs-gbs-auth-msk-scram | FSBI, Single AUTH, Peer Benchmarking | Fully migrated. Downstream validated.
2 | 🟠 HDC / Debit GW | Production | ✅ Complete | DebitGWStreamApp | hdc.debitgw_txn | hdfs:///data/hdc/debitgw/ | Kerberos GSSAPI | ETIMS Cloudera Kafka | cdp-kafka-node01.corp.fiserv.net | 9092 | Parquet | DebitGWStreamDBX | hdc.debitgw_txn | gbs_auth.debitgw_txn_delta | SASL_SSL/SCRAM-SHA-512 | DebitGW_StructStream_Job | b-xxxx.kafka.us-east-1.amazonaws.com:9096 | b-yyyy.kafka.us-west-2.amazonaws.com:9096 | ✅ Live | ✅ Live | Rahul Sharma | Sprint 3 | 2026-01-10 | 2026-02-28 | dbfs:/checkpoints/hdc_debitgw_txn | dcs-gbs-auth-msk-scram | FSBI, AltMOPS | Fully migrated.
3 | 🟡 BUYpass | Production | 🔄 In Progress | BUYpassStreamApp | buypass.auth_txn | hdfs:///data/buypass/auth/ | Kerberos GSSAPI | ETIMS Cloudera Kafka | cdp-kafka-node02.corp.fiserv.net | 9092 | Parquet | BUYpassStreamDBX | buypass.auth_txn | gbs_auth.buypass_auth_delta | SASL_SSL/SCRAM-SHA-512 | BUYpass_StructStream_Job | b-xxxx.kafka.us-east-1.amazonaws.com:9096 | b-yyyy.kafka.us-west-2.amazonaws.com:9096 | 🔄 Testing | 🔄 Testing | Mann Patel | Sprint 4 | 2026-03-01 | 2026-04-15 | dbfs:/checkpoints/buypass_auth_txn | dcs-gbs-auth-msk-scram | Peer Benchmarking, FSBI | Parser re-implementation in review.
4 | 🟢 Omaha | Production | 🔄 In Progress | OmahaStreamApp | omaha.auth_txn | hdfs:///data/omaha/auth/ | Kerberos GSSAPI | ETIMS Cloudera Kafka | cdp-kafka-node02.corp.fiserv.net | 9092 | Parquet | OmahaStreamDBX | omaha.auth_txn | gbs_auth.omaha_auth_delta | SASL_SSL/SCRAM-SHA-512 | Omaha_StructStream_Job | b-xxxx.kafka.us-east-1.amazonaws.com:9096 | b-yyyy.kafka.us-west-2.amazonaws.com:9096 | 🔄 Testing | 📋 Planned | Raneeth Kumar | Sprint 4 | 2026-03-01 | 2026-04-15 | dbfs:/checkpoints/omaha_auth_txn | dcs-gbs-auth-msk-scram | AltMOPS, FSBI | East consumer live. West pending MSK cluster.
5 | 🔵 IPG | Production | 📋 Planned | IPGStreamApp | ipg.auth_txn | hdfs:///data/ipg/auth_txn/ | Kerberos GSSAPI | ETIMS Cloudera Kafka | cdp-kafka-node03.corp.fiserv.net | 9092 | Parquet | IPGStreamDBX | ipg.auth_txn | gbs_auth.ipg_auth_delta | SASL_SSL/SCRAM-SHA-512 | IPG_StructStream_Job | b-xxxx.kafka.us-east-1.amazonaws.com:9096 | b-yyyy.kafka.us-west-2.amazonaws.com:9096 | 📋 Planned | 📋 Planned | Rahul Sharma | Sprint 5 | 2026-04-16 | 2026-06-01 | dbfs:/checkpoints/ipg_auth_txn | dcs-gbs-auth-msk-scram | FSBI, AltMOPS | Awaiting IPG source schema sign-off.
6 | 🟣 FSL | Production | 📋 Planned | FSLTxnStreamApp | fsl.transaction | hdfs:///data/fsl/txn/ | Kerberos GSSAPI | ETIMS Cloudera Kafka | cdp-kafka-node03.corp.fiserv.net | 9092 | Parquet | FSLTxnStreamDBX | fsl.transaction | gbs_auth.fsl_txn_delta | SASL_SSL/SCRAM-SHA-512 | FSLTxn_StructStream_Job | b-xxxx.kafka.us-east-1.amazonaws.com:9096 | b-yyyy.kafka.us-west-2.amazonaws.com:9096 | 📋 Planned | 📋 Planned | Mann Patel | Sprint 5 | 2026-04-16 | 2026-06-01 | dbfs:/checkpoints/fsl_txn | dcs-gbs-auth-msk-scram | Single AUTH | Dependency on FSL schema team.
7 | 🩷 FSL | Production | 📋 Planned | FSLRegStreamApp | fsl.registration | hdfs:///data/fsl/reg/ | Kerberos GSSAPI | ETIMS Cloudera Kafka | cdp-kafka-node03.corp.fiserv.net | 9092 | Parquet | FSLRegStreamDBX | fsl.registration | gbs_auth.fsl_reg_delta | SASL_SSL/SCRAM-SHA-512 | FSLReg_StructStream_Job | b-xxxx.kafka.us-east-1.amazonaws.com:9096 | b-yyyy.kafka.us-west-2.amazonaws.com:9096 | 📋 Planned | 📋 Planned | Mann Patel | Sprint 6 | 2026-06-02 | 2026-07-15 | dbfs:/checkpoints/fsl_reg | dcs-gbs-auth-msk-scram | Peer Benchmarking | Lowest priority. Last in migration sequence.
📊 TOTALS / SUMMARY |  |  | 2 / 7 Done

## ⚙️ Server & Endpoint Config
⚙️ GBS AUTH — Server & Endpoint Configuration ¦ AS-IS vs TO-BE Infrastructure
📌 PLATFORM |  | 📂 AS-IS INFRASTRUCTURE (On-Premises) |  |  |  | 🚀 TO-BE INFRASTRUCTURE (AWS Cloud) |  |  |  |  | 🔐 AUTHENTICATION
Platform | Environment | CDP Cluster | Kafka Broker Host (As-Is) | As-Is Port | As-Is Security Protocol | MSK Cluster Name | MSK East Endpoint (us-east-1) | MSK West Endpoint (us-west-2) | MSK Port | MSK Replication Factor | As-Is Auth Mechanism | To-Be Auth Mechanism | AWS Secrets Manager Key
🔴 HDC.AUTH_TXN | Production | ETIMS Cloudera | cdp-kafka-node01.corp.fiserv.net | 9092 | PLAINTEXT + SASL | dcs-gbs-msk-cluster | b-xxxx.kafka.us-east-1.amazonaws.com:9096 | b-yyyy.kafka.us-west-2.amazonaws.com:9096 | 9096 | 3 | Kerberos GSSAPI | SASL_SSL + SCRAM-SHA-512 | dcs/msk/hdc-auth-creds
🟠 DEBITGW_TXN | Production | ETIMS Cloudera | cdp-kafka-node01.corp.fiserv.net | 9092 | PLAINTEXT + SASL | dcs-gbs-msk-cluster | b-xxxx.kafka.us-east-1.amazonaws.com:9096 | b-yyyy.kafka.us-west-2.amazonaws.com:9096 | 9096 | 3 | Kerberos GSSAPI | SASL_SSL + SCRAM-SHA-512 | dcs/msk/debitgw-creds
🟡 BUYpass.AUTH_TXN | Production | ETIMS Cloudera | cdp-kafka-node02.corp.fiserv.net | 9092 | PLAINTEXT + SASL | dcs-gbs-msk-cluster | b-xxxx.kafka.us-east-1.amazonaws.com:9096 | b-yyyy.kafka.us-west-2.amazonaws.com:9096 | 9096 | 3 | Kerberos GSSAPI | SASL_SSL + SCRAM-SHA-512 | dcs/msk/buypass-creds
🟢 Omaha.AUTH_TXN | Production | ETIMS Cloudera | cdp-kafka-node02.corp.fiserv.net | 9092 | PLAINTEXT + SASL | dcs-gbs-msk-cluster | b-xxxx.kafka.us-east-1.amazonaws.com:9096 | b-yyyy.kafka.us-west-2.amazonaws.com:9096 | 9096 | 3 | Kerberos GSSAPI | SASL_SSL + SCRAM-SHA-512 | dcs/msk/omaha-creds
🔵 IPG.AUTH_TXN | Production | ETIMS Cloudera | cdp-kafka-node03.corp.fiserv.net | 9092 | PLAINTEXT + SASL | dcs-gbs-msk-cluster | b-xxxx.kafka.us-east-1.amazonaws.com:9096 | b-yyyy.kafka.us-west-2.amazonaws.com:9096 | 9096 | 3 | Kerberos GSSAPI | SASL_SSL + SCRAM-SHA-512 | dcs/msk/ipg-creds
🟣 FSL.TRANSACTION | Production | ETIMS Cloudera | cdp-kafka-node03.corp.fiserv.net | 9092 | PLAINTEXT + SASL | dcs-gbs-msk-cluster | b-xxxx.kafka.us-east-1.amazonaws.com:9096 | b-yyyy.kafka.us-west-2.amazonaws.com:9096 | 9096 | 3 | Kerberos GSSAPI | SASL_SSL + SCRAM-SHA-512 | dcs/msk/fsl-txn-creds
🩷 FSL.REGISTRATION | Production | ETIMS Cloudera | cdp-kafka-node03.corp.fiserv.net | 9092 | PLAINTEXT + SASL | dcs-gbs-msk-cluster | b-xxxx.kafka.us-east-1.amazonaws.com:9096 | b-yyyy.kafka.us-west-2.amazonaws.com:9096 | 9096 | 3 | Kerberos GSSAPI | SASL_SSL + SCRAM-SHA-512 | dcs/msk/fsl-reg-creds

## 📊 Topic & Table Mapping
📊 GBS AUTH — Topic & Table Mapping ¦ As-Is Kafka Topics & HDFS Paths → To-Be MSK Topics & Delta Tables
📌 PLATFORM |  | 📂 AS-IS (Cloudera / HDFS) |  |  |  | 🚀 TO-BE (MSK / Delta Lake) |  |  |  | 📋 GOVERNANCE
Platform | Environment | As-Is Kafka Topic | As-Is HDFS Path | As-Is Partitioning | As-Is Format | To-Be MSK Topic | To-Be Delta Table (Unity Catalog) | Delta Partitioning | DBX Job Name | Consumers | Topic Status | Notes
🔴 HDC.AUTH_TXN | Production | hdc.auth_txn | hdfs:///data/hdc/auth_txn/ | year/month/day | Parquet | hdc.auth_txn | gbs_auth.hdc_auth_delta | region/year/month/day | HDCAuth_StructStream_Job | FSBI, Single AUTH | ✅ Complete
🟠 DEBITGW_TXN | Production | hdc.debitgw_txn | hdfs:///data/hdc/debitgw/ | year/month/day | Parquet | hdc.debitgw_txn | gbs_auth.debitgw_txn_delta | region/year/month/day | DebitGW_StructStream_Job | FSBI, AltMOPS | ✅ Complete
🟡 BUYpass.AUTH_TXN | Production | buypass.auth_txn | hdfs:///data/buypass/auth/ | year/month/day | Parquet | buypass.auth_txn | gbs_auth.buypass_auth_delta | region/year/month/day | BUYpass_StructStream_Job | Peer Benchmarking | 🔄 In Progress | Schema review pending
🟢 Omaha.AUTH_TXN | Production | omaha.auth_txn | hdfs:///data/omaha/auth/ | year/month/day | Parquet | omaha.auth_txn | gbs_auth.omaha_auth_delta | region/year/month/day | Omaha_StructStream_Job | AltMOPS | 🔄 In Progress | West cluster pending
🔵 IPG.AUTH_TXN | Production | ipg.auth_txn | hdfs:///data/ipg/auth_txn/ | year/month/day | Parquet | ipg.auth_txn | gbs_auth.ipg_auth_delta | region/year/month/day | IPG_StructStream_Job | FSBI, AltMOPS | 📋 Planned | Awaiting schema sign-off
🟣 FSL.TRANSACTION | Production | fsl.transaction | hdfs:///data/fsl/txn/ | year/month/day | Parquet | fsl.transaction | gbs_auth.fsl_txn_delta | region/year/month/day | FSLTxn_StructStream_Job | Single AUTH | 📋 Planned | Dependency: FSL team
🩷 FSL.REGISTRATION | Production | fsl.registration | hdfs:///data/fsl/reg/ | year/month/day | Parquet | fsl.registration | gbs_auth.fsl_reg_delta | region/year/month/day | FSLReg_StructStream_Job | Peer Benchmarking | 📋 Planned | Lowest priority

## 📈 Dashboard
📈 GBS AUTH Migration — Executive Dashboard
📦 Total Platforms |  |  | ✅ Completed |  |  | 🔄 In Progress |  |  | 📋 Planned | 🎯 Migration Progress
7 |  |  | 2 / 7 Done |  |  | 2 |  |  | 3 | 28.57%
Platform | Existing App | New App | MSK Topic | Delta Table | Owner | Sprint | Status | East | West
🔴 HDC.AUTH_TXN | HDCAuthStreamApp | HDCAuthStreamDBX | hdc.auth_txn | gbs_auth.hdc_auth_delta | Raneeth Kumar | Sprint 3 | ✅ Complete | ✅ Live | ✅ Live
🟠 DEBITGW_TXN | DebitGWStreamApp | DebitGWStreamDBX | hdc.debitgw_txn | gbs_auth.debitgw_txn_delta | Rahul Sharma | Sprint 3 | ✅ Complete | ✅ Live | ✅ Live
🟡 BUYpass.AUTH_TXN | BUYpassStreamApp | BUYpassStreamDBX | buypass.auth_txn | gbs_auth.buypass_auth_delta | Mann Patel | Sprint 4 | 🔄 In Progress | 🔄 Test | 🔄 Test
🟢 Omaha.AUTH_TXN | OmahaStreamApp | OmahaStreamDBX | omaha.auth_txn | gbs_auth.omaha_auth_delta | Raneeth Kumar | Sprint 4 | 🔄 In Progress | 🔄 Test | 📋 Plan
🔵 IPG.AUTH_TXN | IPGStreamApp | IPGStreamDBX | ipg.auth_txn | gbs_auth.ipg_auth_delta | Rahul Sharma | Sprint 5 | 📋 Planned | 📋 Plan | 📋 Plan
🟣 FSL.TRANSACTION | FSLTxnStreamApp | FSLTxnStreamDBX | fsl.transaction | gbs_auth.fsl_txn_delta | Mann Patel | Sprint 5 | 📋 Planned | 📋 Plan | 📋 Plan
🩷 FSL.REGISTRATION | FSLRegStreamApp | FSLRegStreamDBX | fsl.registration | gbs_auth.fsl_reg_delta | Mann Patel | Sprint 6 | 📋 Planned | 📋 Plan | 📋 Plan

## 📖 Legend & Guide
📖 GBS AUTH Migration Tracker — Legend, Colour Guide & Field Descriptions
🎨 ROW STATUS COLOURS |  | 📋 FIELD DESCRIPTIONS
✅ Complete | Migration fully done. Consumers validated. Live in production. | Existing App Name
🔄 In Progress | Active development or testing phase. East or West consumer may be live. | Existing Kafka Topic
📋 Planned | Not yet started. Waiting for sprint allocation or dependency resolution. | Existing Table/Path
🚫 Blocked | Migration halted due to a blocker. See Notes column for details. | Existing Auth
New App Name
New Kafka Topic
New Delta Table
DBX Job Name
MSK East Endpoint
MSK West Endpoint
SASL_SSL/SCRAM-512
DBX Secret Scope
DBFS Checkpoint
East/West Status